## Sheet1
Theme | As a/an... | I want to... | So that... | Notes | Priority (1-5) | Estimation (1-5) | Status
Visit Journal | Mother | keep track of my oncology appointment dates and times | I can get to all of them on time | upcoming appointments need to be in visit journal, notifications? | 1 | 4
Recording | Mother | record the appointment | I can make sure I remember everything doctors say | recording appointment(voice recognition) | 5 | 4
Visit Journal | Mother | have a summary of the appointment info | I can organized those info | summary visit journal (machine learning)/ out of scope of our project | 1 | 5
Forget Password | Older patient | find my password back easily if I forgot my password | I can access my account | forget password page | 5 | 3
Login Page | Older patient | easily log in to my account | I can see details about past/upcoming clinical visits on my own | PIN login feature / simple interface that is easy to navigate | 5 | 2
Sign Up Page | Older patient | sign up easily | I can use the app | Sign up page, what information we need for signing up? | 5 | 2
User Account | Older patient | keep track of past hospitals and personal information | I can access / utilize that information during appointments | upload insurance information, address, date of birth (dropdown menu on recording) | 3 | 3
Contact | Patient | be able to find the contact info for my current and past physicians | I can ask them direct questions about my condition | Put this in user profile | 3 | 2
Education | Patient | learn more about the app and how I should use it | I can get the most out of my appointments | Cornelius FAQ page | 4 | 1
Education | Patient | get answers to questions other patients have asked in my shoes | I can be more prepared and educated about my prognosis | Patient FAQ page | 2 | 5
User Account | Patient | update my personal information like my insurance and contact | my information is up-to-date when I make decisions later | Update user profile (PUT requests) | 3 | 2
Visit Journal | ESL Patient | be able to translate my visit journal into another language | I can read my journal in my native language | Cloud translation APIs (google), maybe outside project scope | 1 | 3
Visit Journal | Patient | search my visit journals by date | I can remember a part of a specific appointment |  | 2 | 4